Samara Sculpture Timeline (Updated 7/23)

|  |  |  |
| --- | --- | --- |
| **Applicant and/or Organization Name:** Havre de Grace Arts Collective | | |
| **Date From: (month)** | **Date To: (month)** | **Activity/Task** |
| April 2023 |  | Project Grant proposal for sculpture installation submitted. |
| June 2023 |  | Notification of Project Grant award status. |
| July 2023 |  | Finalize details and execute contract between artists and the city. |
| August 2023 |  | Grant money becomes available - |
|  |  | 50% artist cost disbursed to artists ($22,500). Materials ordered. |
| Sept. 2023 | Jan. 2024 | Artists begin and continue work on sculpture fabrication. |
| Jan. 2024 |  | Progress check-in with MSAC and HdG Arts Collective - |
|  |  | studio visit(s), photographs of progress shared, plaque ordered. |
|  |  | 25% artist cost distributed to artists ($11,250). |
| Jan. 2024 | April 2024 | Fabrication of sculpture completed. |
| March 2024 | April 2024 | Installation of concrete footer for capstan base |
| April 2024 | May 2024 | Installation of capstan and 5” concrete base pad |
| May 2024 |  | Sculpture installed; plaque installed. |
| May 2024 | June 2024 | Sculpture unveiled in a public ceremony. |
|  |  | Photo documentation. |
|  |  | Final 25% artist cost distributed to artists ($11,250). |
|  |  | City of Havre de Grace and the Havre de Grace Arts Collective |
|  |  | assume responsibility for the sculpture. |
| June 2024 | July 2024 | Final report completed by the Havre de Grace Arts Collective. |
|  |  |  |